## Sheet1
Sleep Diary App Risk Register | [6 empty] | Template from: https://www.leadingagile.com/
| Positive Risk Response Options | Exploit | Share | Enhance | Accept |  | Risk | Something which has not happened, but might
| Negative Risk Response Options | Avoid | Transfer | Mitigate | Accept |  | Issue | Something which has already happened
| Alternate Response Options | Contingency |  |  |  |  | No longer active
Risk ID | Description | Risk Owner | Risk Trigger | Risk Category | Probability (1-3) | Impact (1-3) | PI Score | Expected Result, No Action | Risk Response Type | Response Description
| Description of the risk | Name of person who monitors the risk and initiates response | How you know the risk is becoming an issue or has reached a point that requires action. | Group defines the types of risks (technology, financial, staffing, etc.) | Group sourced rough estimate of how likely this is to occur | Group sourced rough estimate of how significant the impact of this risk will be if/when it becomes an issue | Probability multiplied by Impact | What will happen if the risk becomes an issue and no action is taken | Decision made by group on how to respond to this risk (see above in blue) | What is the response
S1 | Effort put into unnecessary content | David Yu | If an idea or content is presented to the client and deemed unwanted | Scope | 2 | 2 | 4 | Time will have been wasted which could have been more productive. | Avoid | Confirm with client exact bounds, update scope of work if necessary and cease any further work on feature.
S2 | Unmet client expectaions | David Yu | If content is presented to the client but deemed lacking. | Scope | 1 | 3 | 3 | Product unusable, client gives poor review to the team. | Avoid | Confirm with client exact bounds, update scope of work if necessary and cease any further work on feature.
M1 | Cost (over time budget) | Michael Dorrell | If more hours are spent on the project than anticipated | Financial | 3 | 2 | 6 | Team overworked and suffer in other units. | Mitigate | Determine allowable extra hours, drop stretch goals and/or others goals as necessary.
M2 | Time | Michael Dorrell | If task(s) are taking longer than expected or available time is reduced (e.g. by member work/study). | Financial | 2 | 3 | 6 | Task not completed. | Mitigate/transfer | Redistribute work and/or spend more time if possible.
M3 | Completion (goals not met) | Michael Dorrell | If it is calculated that there is not enough time to complete particular goal(s). | Management | 2 | 3 | 6 | Project not completed. | Avoid | Determine most appropriate goals to drop, starting from stretch goal, drop and reallocate remaining work.
M4 | Member participation | Joshua Pollard | If member(s) are working noticeably below average hours or has no current task assigned. | Team dynamics | 1 | 3 | 3 | Overall quality drops, and/or other members overworked. | Avoid | If no assigned task, assign new task. If not working, address issue and try resolve by encouraging work or providing support between members.
M5 | Member communication | Joshua Pollard | If there is inadequate communication between members. | Team dynamics | 1 | 2 | 2 | Tasks overlooked or not completed. Same work repeated by different members. | Avoid | Address issue and make communication means and expectations clear.
M6 | Client communication | David Yu | If there is inadequate communication with the client or barriers to said communication. | Management | 1 | 3 | 3 | Tasks unclear and not met. Effort wasted. | Avoid | Try to remove barriers, keep attempting to communicate. If necessary meet in person and address issue directly.
M7 | Sickness | Michael Dorrell | If any work is or will be disrupted by sickness. | Management | 2 | 2 | 4 | Member tasks not done or rushed. | Transfer | Redistribute work as appropriate.
M8 | Study/Assignments | Michael Dorrell | If any work is or will be disrupted by other units. | Management | 3 | 2 | 6 | Member tasks not done or rushed. | Transfer | Aim to perform more work at other times to compensate for lost time. Redistribute work as appropriate.
M9 | Work | Michael Dorrell | If any work is or will be disrupted by other work. | Management | 2 | 2 | 4 | Member tasks not done or rushed. | Transfer | Aim to perform more work at other times to compensate for lost time. Redistribute work as appropriate.
T1 | Performance | Adam Chambost | If any function of the project does not work as intended or found to use an unacceptable amount of resources (e.g. is too slow) | Testing | 1 | 2 | 2 | Product unusable, client gives poor review to the team. | Mitigate | Attempt to reduce as much as possible by using alternative solutions and seek to maximize performance.
T2 | Usability | Joshua Pollard | If developed functions are found to be to complicated or otherwise difficult to use by intended users. | Testing | 1 | 3 | 3 | Product unusable, client gives poor review to the team. | Avoid | Attempt to simplify GUI as much as possible and redesign as necessary.
T3 | Maintenance | Zihao Liu | If a function is determined to require maintenance in order to continue to work over time | Long term | 1 | 1 | 1 | Product becomes unusable over time. | Mitigate | Seek alternatives, if no better solution feasable then set up action plan for when the problem arises.
T4 | User security | Taige Liu | If there is found to be any possible breach of user privacy with the current system. | Security | 2 | 3 | 6 | User information is obtained and misussed by 3rd parties, legal action taken. | Avoid | Resolve issue if at all possible. If not possible, reduce risk as much as possible and seek alternative methods.
T5 | Data sensitivity | Taige Liu | If any data is found to be stored or communicated in an inappropriate format. | Security | 2 | 3 | 6 | User information is obtained and misussed by 3rd parties, legal action taken. | Avoid | Resolve issue if at all possible. If not possible, reduce risk as much as possible and seek alternative methods.
T6 | System security | Taige Liu | If the system itself is found to be vunerable to security breach. | Security | 2 | 3 | 6 | System information is obtained and system broken by 3rd parties. | Avoid | Resolve issue if at all possible. If not possible, reduce risk as much as possible and seek alternative methods.
T7 | Cross platform complications | Zihao Liu | If cross mobile platform support is determined to be infeasible. | Technical | 3 | 3 | 9 | Two incomplete apps produced. | Avoid | Have primary platform (iOS) and drop alternative platform and focus team solely on primary platform.
T8 | Unforeseen technical complications | Adam Chambost | If any technical aspect of production is determined to negatively influence overall production is discovered. | Technical | 2 | 2 | 4 | Product not completed. | Mitigate | Attempt to solve and/or find alternative solutions.
T9 | Unbalanced progress (i.e. can't implement A until B is completed) | Zihao Liu | If it is determined that the current division of labour is insufficient and can be improved. | Management | 2 | 2 | 4 | Product not completed. | Transfer | Reallocating subgroup members and/or division of labour as appropriate.
T10 | Resource availability | Adam Chambost | If the planned resources to complete a task are unavailable or otherwise unusable. | Technical | 2 | 2 | 4 | Product not completed. | Avoid | Seek alternative resources.
T11 | Legal issues | David Yu | If any function is discovered to have any legal issue that must be addressed. | Legal | 1 | 3 | 3 | Legal action taken by offended party against group. | Avoid | Resolve issue immediately.
T12 | Copyright issues | Zihao Liu | If material used or intended to be used are discovered to breach copyright for any reason. | Legal | 1 | 3 | 3 | Legal action taken by offended party against group. | Avoid | Resolve issue immediately.