## Sheet1
Sleep Diary App Risk Register | [6 empty] | Template from: https://www.leadingagile.com/
| Positive Risk Response Options | Exploit | Share | Enhance | Accept |  | Risk | Something which has not happened, but might
| Negative Risk Response Options | Avoid | Transfer | Mitigate | Accept |  | Issue | Something which has already happened
| Alternate Response Options | Contingency |  |  |  |  | No longer active
Risk ID | Description | Risk Owner | Risk Trigger | Risk Category | Probability (1-3) | Impact (1-3) | PI Score | Expected Result, No Action | Risk Response Type | Response Trigger | Response Owner | Response Description | Expected Impact of Response
| Description of the risk | Name of person who monitors the risk | How you know the risk is becoming an issue or has reached a point that requires action. | Group defines the types of risks (technology, financial, staffing, etc.) | Group sourced rough estimate of how likely this is to occur | Group sourced rough estimate of how significant the impact of this risk will be if/when it becomes an issue | Probability multiplied by Impact | What will happen if the risk becomes an issue and no action is taken | Decision made by group on how to respond to this risk (see above in blue) | How do you know it is time to put the response into play | Who is responsible for initiating the response | What is the response | What do you expect will result from the response
EXAMPLE | There is a chance that the project cost will exceed the amount that the company has budged for the work. | Joe Agileguy | If the expected work remaining will cost more than $9,000 over budget we will need to seek additional funding from management. | Financial | 2 | 3 | 6 | We will not be able to secure funding necessary to complete the project. Work may stop before MVP has been achieved. Product may never get to market and be deemed a total failure. | Mitigate | When estimated cost for MVP is within 5K of approved project total we will begin seeking additional funding. | Jimmy Kanban | Meet with key stakeholders to review finished product, total spend to date, work remaining and expected total spend. Ask for additional funding to complete work. | Given that our team has a mostly stable velocity, a proven ability to meet commitments and deliver value, we expect the answer to be yes provided the total amount requests is less than $25K.
S1 | Effort put into unnecessary content | TBD | If an idea or content is presented to the client and deemed unwanted | Scope | 2 | 2 | 4 | Time will have been wasted which could have been more productive. | Avoid |  | TBD
S2 | unmet client expectaions | TBD | If content presented to the client and deemed lacking. | Scope | 1 | 3 | 3 | Product unusable, client gives poor review to the team. | Avoid |  | TBD
M1 | cost (over budget) | TBD | If more hours are spent on the project than anticipated | Financial | 3 | 2 | 6 | Team overworked and suffer in other units. | Mitigate |  | TBD
M2 | time | TBD | If task(s) are taking longer than expected or available time is reduced (e.g. by member work/study). | Financial | 2 | 3 | 6 | Task not completed. | Mitigate/transfer |  | TBD
M3 | completion (goals not met) | TBD | If it is calculated that there is not enough time to complete particular goal(s). | Management | 2 | 3 | 6 | Project not completed. | Avoid |  | TBD
M4 | Member participation | TBD | If member(s) are working noticeably below average hours or has no current task assigned. | Team dynamics | 1 | 3 | 3 | Overall quality drops, and/or other members overworked. | Avoid |  | TBD
M5 | Member communication | TBD | If there is inadequate communication between members. | Team dynamics | 1 | 2 | 2 | Tasks overlooked or not completed. Same work repeated by different members. | Avoid |  | TBD
M6 | Client communication | TBD | If there is inadequate communication with the client or barriers to said communication. | Management | 1 | 3 | 3 | Tasks unclear and not met. Effort wasted. | Avoid |  | TBD
M7 | Sickness | TBD | If any work is or will be disrupted by sickness. | Management | 2 | 2 | 4 | Member tasks not done or rushed. | Transfer |  | TBD
M8 | Study/Assignments | TBD | If any work is or will be disrupted by other units. | Management | 3 | 2 | 6 | Member tasks not done or rushed. | Transfer |  | TBD
M9 | Work | TBD | If any work is or will be disrupted by other work. | Management | 2 | 2 | 4 | Member tasks not done or rushed. | Transfer |  | TBD
T1 | performance | TBD | If any function of the project does not work as intended or found to use an unacceptable amount of resources (e.g. is too slow) | Testing | 1 | 2 | 2 | Product unusable, client gives poor review to the team. | Mitigate |  | TBD
T2 | usability | TBD | If developed functions are found to be to complicated or otherwise difficult to use by intended users. | Testing | 1 | 3 | 3 | Product unusable, client gives poor review to the team. | Avoid |  | TBD
T3 | maintenance | TBD | If a function is determined to require maintenance in order to continue to work over time | Long term | 1 | 1 | 1 | Product becomes unusable over time. | Mitigate |  | TBD
T4 | User security | TBD | If there is found to be any possible breach of user privacy with the current system. | Security | 2 | 3 | 6 | User information is obtained and misussed by 3rd parties, legal action taken. | Avoid |  | TBD
T5 | data sensitivity | TBD | If any data is found to be stored or communicated in an inappropriate format. | Security | 2 | 3 | 6 | User information is obtained and misussed by 3rd parties, legal action taken. | Avoid |  | TBD
T6 | system security | TBD | If the system itself is found to be vunerable to security breach. | Security | 2 | 3 | 6 | System information is obtained and system broken by 3rd parties. | Avoid |  | TBD
T7 | Cross platform complications | TBD | If cross mobile platform support is determined to be infeasible. | Technical | 3 | 3 | 9 | Two incomplete apps produced. | Avoid |  | TBD
T8 | Unforeseen technical complications | TBD | If any technical aspect of production is determined to negatively influence overall production is discovered. | Technical | 2 | 2 | 4 | Product not completed. | Mitigate |  | TBD
T9 | Unbalanced progress (i.e. can't implement A until B is completed) | TBD | If it is determined that the current division of labour is insufficient and can be improved. | Management | 2 | 2 | 4 | Product not completed. | Transfer |  | TBD | Reallocating subgroup members and/or division of labour as appropriate.
T10 | Resource availability | TBD | If the planned resources to complete a task are unavailable or otherwise unusable. | Technical | 2 | 2 | 4 | Product not completed. | Avoid |  | TBD
T11 | Legal issues | TBD | If any function is discovered to have any legal issue that must be addressed. | Legal | 1 | 3 | 3 | Legal action taken by offended party against group. | Avoid |  | TBD
T12 | Copyright issues | TBD | If material used or intended to be used are discovered to breach copyright for any reason. | Legal | 1 | 3 | 3 | Legal action taken by offended party against group. | Avoid |  | TBD